## Sheet1
This WBS/Estimation is a draft .This estimate is subject to changes if any additional functionality is required or if we are missing any details in requirements
Sprint | Epic / Story ID | EPIC & Story Description | Effort Estimate(Person Hours) |  |  | Status | Actual Effort (Man Days) |  |  | Remarks
|  |  | DevOps** | Backend ** | QA ** |  | DevOps ** | Backend ** | QA **
Sprint 1 |  | Project Setup
| Story-1 | Project basic structure definition | 10 Hours | 70 Hours
| Story-2 | Git Setup
| Story-3 | Server Setup
| Story-4 | - SonarQube
| Story-5 | Theme Setup
| Story-6 | Project setup on Local Machine
| Story-7 | Code Deployed On Development Server
| Story-8 | Home page designed
| Story-9 | create header, footer design
| Story-10 | Woocommerce Setup
| Story-11 | Create Pages With Design About US, contact us, Shop page, prdouct page
| Story-12 | Create pages from Wp-admin,
| Story-13 | add products from admin
Sprint 2 |  | dynamic menus,Add Dummytext,desined
| Story-14 | Dynamic Menus Creation and add from wp-admin Shows in header and Main menu banner menu | 8 | 72
| Story-15 | Add 10 Dummy Products and add Dummy Text On the website
| Story-16 | Add logo Dynamiclly
| Story-17 | Search functionality for products and product catogries
| Story-18 | Create Shop page
| Story-19 | Create A single Product Pages
| Story-20 | Design issues
| Story-21 | Add product brands
Sprint 3 |  | Login/signup for woocommerce
| Story-21 | Login/signup for woocommerce | 5 Hours | 75 Hours | 10 Hours
| Story-22 | Add Swatches On product
| Story-23 | Add Filter On Shop Page
| Story-24 | Mail functionality through Smtp New order, Cancelled order,Failed order,Order on-hold Processing order,Shipped Order,Refunded order,Reset password,New account Delivered order,Failed Subscription Renewal SCA Authentication,Payment Authentication Requested Emai
| Story-25 | Add Contact Forms with sent email to Admin * Footer * Contact Us page
Sprint 4 |  | multivendor
| Story-26 | Add Multivendor Dokan User Crearte Vendor,User can upload the data from Frontend on self account,Design,Admin Account Crated ,All Product show,order page for vendor,authntication for registeration | 5 Hours | 75 Hours
| Story-27 | add 5 to 6 mega menus in header
| Story-28 | Add otp verification for number woocommerce in my account
| Story-29 | Review Functionality
| Story-30 | if user will not added review Than by default show null reveiw
| Story-31 | single product
| Story-32 | product listing
| Story-33 | change layout of shop page
Sprint 5 |  | mobile resposive
| Story-34 | If show On website Placed Select option and read more than It will Show Add to Cart If Admin Or Vandor Prdoct is purchasable |  | 80 hours
| Story-35 | website is mobile responsive
| Story-36 | Production website if development server is working fine
| Story-37 | Devops Work
| Story-38 | payment gatway integration
| Story-39 | All Are Mobile Responisve
| Story-40 | Create 10 page (Added Dummt Text on the Website) Contact us,About Us,Payments,Shipping,Cancellations and Returns,FAQ,Report Infringement,Return Policy,Terms of use,Secuirty,Privacy,Sitemap
| Story-41 | Create 5 seprate page 1. on sale product 2. show latest product 3. Best Selling Product 4. Top rated products 5. Featured Products
Sprint 6 |  | Notification
| Story-42 | Added product 100 + catagories |  | 80
| Story-43 | create a saprate categories page with design
| Story-44 | Add to cart functionality
| Story-45 | place order
| Story-46 | payment with checkout page
| Story-47 | Add Wishlist functionality
| Story-48 | add 4 words showing production listinh on homepage functionality
| Story-49 | Add filters on the shop page and admin can custmize the website
| Story-50 | Add popup in header it will show dropdown menu * my Acoount * My Order * logout
| Story-51 | add view all button on home page all on sale, latest product, top rated, featured product linkinng on saprate page
| Story-52 | order tracking
| Story-53 | Multivendor page Design with mobile responsive
Sprint 7 |  | admin report status slider,website issue Fixed after testing
|  |  |  | 60 hours | 10 Hours
| Story-54 | added 4 sliders on home page
| Story-55 | Admin Can Change Order Status processing delivered shipped refunded
| Story-56 | admin can check report of earning on the website
| Story-57 | shipping provider
| Story-58 | admin can check report of earning on the website
| Story-59 | If admin or vendor want to cancle order than both can cancle on order page
| Total Hours | 540 hours